## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.1 | As an investor, I want to request from an admin a lawyer to be assigned to fill a form on behalf of me | 3 | Mostafa Waleed | Omar Bakr | Ahmed Ashraf
1.2 | As an investor, I want to view the contact info of my assigned lawyer | 2 | Omar Bakr | Ahmed Ashraf | Omar Khaled
2.1 | As an investor, I want to view the fees of my application | 2 | Ahmed Ashraf | Omar Khaled | Yosri Khaled
3.1 | As a lawyer or investor, I want to receive a notification whenever the company establishment is finished | 5 | Ahmed Ashraf | Omar Khaled | Yosri Khaled
3.2 | As a lawyer or investor, I want to receive a notification whenever a comment is placed on my company | 5 | Omar Khaled | Yosri Khaled | Beeshoy Raef
3.3 | As a lawyer, I want to receive a notification whenever I get assigned to a company application | 5 | Yosri Khaled | Beeshoy Raef | Ahmed Osama
4.1 | As an admin, I want to view a list of paid applications | 3 | Ahmed Osama | Beeshoy Raef | Omar El Desouki
5.1 | As an admin, I want to view a list of unassigned applications | 3 | Beeshoy Raef | Omar El Desouki | Abed Hossam
5.2 | As an admin, I want to assign an unassigned application to any lawyer | 3 | Omar El Desouki | Ahmed Osama | Omar Bakr
5.3 | As an admin, I want to view a list of unreviewed applications | 3 | Ahmed Osama | Abed Hossam | Mostafa Waleed
5.4 | As an admin, I want to assign an unreviewed application to any reviewer | 3 | Abed Hossam | Mostafa Waleed | Omar Bakr