## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | User accounts
1.1 | As an investor, I want to create my account | 5 | Omar Bakr
1.2 | As an admin, I want to create an account for entity employees | 5 | Omar Bakr
1.3 | As a logged in user, I want to view my profile info | 3 | Omar Bakr | 1.1
1.4 | As an investor, I want to view the contact info of my assigned lawyer | 2 | Omar Desouki | 1.2
1.5 | As an admin, I want to view the profile info of any user | 2 | Beeshoy Raef | 1.1
1.6 | As an investor, I want to update my profile info | 5 | Omar El Desouki | 1.1
1.7 | As an admin, I want to update the profile info of any user | 5 | Beeshoy Raef | 1.2
1.8 | As a user, I should be able to create my account then view or update it | 1 | Omar Bakr | 1.1, 1.3, 1.6 | Yes
1.9 | As an admin, I should be able to create the account for any entity employee then view or update it | 1 | Omar Bakr | 1.2, 1.5, 1.7 | Yes
2 | Company applications
2.1 | As an investor or a lawyer, I want to create a company application | 5 | Yosri Khaled
2.2 | As an investor or a lawyer, I want to view my company application | 3 | Ahmed Ashraf | 2.1
2.3 | As an admin, I want to view all company applications | 3 | Omar Khaled | 2.1
2.4 | As an investor or a lawyer, I want to update my company application | 5 | Ahmed Ashraf | 2.1
2.5 | As an investor or a lawyer, I want to delete my company application | 3 | Omar Khaled | 2.1
2.6 | As an admin, I want to delete any company application | 3 | Yosri Khaled | 2.1
2.7 | As an investor or a lawyer, I should be able to create a company application the view, update or delete it | 1 | Yosri Khaled | 2.1, 2.2, 2.4, 2.5 | Yes
2.8 | As an admin, I should be able to view any created company application and delete it | 1 | Yosri Khaled | 2.3, 2.6 | Yes
3 | Comments
3.1 | As a lawyer or a reviewer I want to create a comment | 3 | Mostafa Waleed
3.2 | As a user I want to retrieve a comment | 2 | Mostafa Waleed | 3.1
3.3 | As a lawyer or a reviewer I want to update a comment I created | 3 | Mostafa Waleed | 3.1
3.4 | As lawyer or a reviewer I want to delete a comment I created | 2 | Mostafa Waleed | 3.1
4 | Notifications
4.1 | As a user, I want a notification to be created whenever an action is required | 3 | Abed Hossam
4.2 | As a user, I want to view my notifications | 2 | Abed Hossam | 4.1
5 | Electronic Journals
5.1 | As a unregistered user, I want to have an electronic journal created for every established company | 5 | Ahmed Osama
5.2 | As a unregistered user i want to view the electronic journal for every existing established company | 8 | Ahmed Osama | 5.1