## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Board members
1.1 | As a user, I can view the board members of an application | 2 | Omar El Desouki | Mostafa Waleed | Beshoy Raef
1.2 | As an investor or lawyer, I can add or edit board members when creating an application | 5 | Omar Khaled | Omar El Desouki | Mostafa Waleed
1.3 | As an investor or lawyer, I can edit board members of my application | 5 | Omar Abdallah | Omar Khaled | Omar El Desouki
2 | Frontend changes
2.1 | As an external entity user, I should be redirected to an admin portal when logging in | 5 | Ahmed Osama | Omar Abdallah | Omar Khaled
2.2 | As a user, I can edit or delete my comments | 3 | Yosri Khaled | Ahmed Osama | Omar Abdallah
2.3 | As a user, I can delete my company application | 2 | Abed Hossam | Yosri Khaled | Ahmed Osama
3 | Backend
3.1 | Authentication for user controller | 5 | Ahmed Ashraf | Abed Hossam | Yosri Khaled
3.2 | Authentication for company controller | 5 | Beshoy Raef | Ahmed Ashraf | Abed Hossam
3.3 | Authentication for other controllers | 5 | Mostafa Waleed | Beshoy Raef | Ahmed Ashraf